## Prepare for Installation
Step | Description | Role | Time Estimate | Status
Review the Zowe CLI Information Roadmap | Learn about various Zowe CLI topics. | Systems Administrator Application Developer Systems Programmer DevOps Architect | 15 minutes
Review the Release Notes | Read about new features and enhancements included with the latest release of Zowe CLI. | Systems Administrator Application Developer Systems Programmer DevOps Architect | 15 minutes
Address System Requirements | Install the client-side and host-side software, and ensure that there is sufficient free disk space. | Systems Administrator | See Note 1
(Optional) Install API Mediation Layer | Install the Zowe Runtime, which includes the API Mediation Layer. | Systems Administrator | 8 hours
Install z/OSMF | Follow these steps to install z/OSMF. | Systems Administrator | See Note 2
Determine Profile Types | Learn about configuration and how to use team profiles. | Systems Administrator DevOps Architect | 15 minutes
Note 1: Allow 15 minutes to install the client-side software. The amount of time to install the host-side software depends upon your site's implementation. For example, do you require z/OSMF, REST APIs, or both, to support the Mediation Layer? See the information for the specific server-side software that you require to determine how much time to allow for complete server-side installation and configuration.
Note 2: Allow 15 to 25 hours to install and configure z/OSMF. The length of time varies depending on the External Security Manager (ESM) that you are running in your site.

## Install Zowe CLI
Step | Description | Role | Time Estimate | Status
Install Zowe CLI | Install Zowe CLI from an online registry or a local package. | Systems Administrator | 30 minutes
Install Zowe CLI (Quick Start) | Use the Quick Start method if you possess prerequisite knowledge of command line tools and writing scripts, and you want to get started with Zowe CLI quickly and easily. | Systems Administrator | 15 minutes
(Optional) Install Zowe CLI plug-ins | Install Zowe CLI plug-ins from an online registry or a local package. | Systems Administrator | 15 minutes

## Configure Zowe CLI
Step | Description | Role | Time Estimate | Status
Configure environment variables | Learn how to store configuration options that are common to your environment. | Systems Administrator DevOps Architech Application Developer | 15 minutes
Configure Zowe profiles | Learn how to configure Zowe team profiles and user profiles. | Systems Administrator DevOps Architech Application Developer | 15 minutes
Configure daemon mode | Learn how to configure Zowe CLI to run as persisten background process (daemon). | Systems Administrator DevOps Architech Application Developer | 15 minutes